## Sheet1
Action Item | Responsible Party | Days | Date | Notes
Secure Trip Date (Add to Spreadsheet in Yellow Box) | Host Church Team Leader & For the City
Registration built in Landmark PCO | Landmark Administrator
Applications and Trip Roll Out | Host Church Team Leader | -150 | 2023-05-03
Applications due / Vetting Begins | Host Church Team Leader | -120 | 2023-06-02
Deposits due | Host Church Team Leader & Landmark Administrator | -90 | 2023-07-02
Team Roster Set and Final payments dues | Host Church Team Leader & Landmark Administrator | -60 | 2023-08-01
Medical credentials and documents to field for medical team (if applicable) | GB Global Missions | -60 | 2023-08-01
Determine Special Projects based off Team Roster (if applicable) | Host Church Team Leader & For the City | -50 | 2023-08-11
Determine Fun Day | Host Church Team Leader & For the City | -50 | 2023-08-11
Send names and numbers (total, male, female) including ages to field | GB Global Missions | -45 | 2023-08-16
Ensure all ticket information is correct | Host Church Team Leader | -45 | 2023-08-16
Host Small Group Week 1 | Host Church Team Leader | -35 | 2023-08-26
Host Small Group Week 2 | Host Church Team Leader | -30 | 2023-08-31
Ensure that all visas are seccured if required | GB Global Missions | -30 | 2023-08-31
Send out e-ticket information to team leader | GB Global Missions | -30 | 2023-08-31
Host Small Group Week 3 | Host Church Team Leader | -25 | 2023-09-05
Host Small Group Week 4 | Host Church Team Leader | -20 | 2023-09-10
Host Small Group Week 5 | Host Church Team Leader | -15 | 2023-09-15
Send food money and project money to field | GB Global Missions | -15 | 2023-09-15
Travel insurance obtained and cards sent to team leader | GB Global Missions | -15 | 2023-09-15
Team t-shirts sent to team leaders | GB Global Missions | -15 | 2023-09-15
Register team with US Department of State (SMART) | GB Global Missions | -15 | 2023-09-15
Send project money received less than 14 days prior to field immediately | GB Global Missions | -14 | 2023-09-16
Host Small Group Week 6 | Host Church Team Leader | -10 | 2023-09-20
Host Small Group Week 7 | Host Church Team Leader | -5 | 2023-09-25
Trip Date |  |  | 2023-09-30
Host Small Group Lesson 8 | Host Church Team Leader
Host Small Group Leson 9 | Host Church Team Leader
Fun Day | Activity ???
Share Recap Video at Church / Promo Next Trip | Host Church Team Leader | 8 | 2023-10-08
Host Small Group Week 10 | Host Church Team Leader | 12 | 2023-10-12
Formulas:
Date = SUM(D27,[Days])
Date = SUM([Date, row below],[Days])