## Sheet1
Action Item | Responsible Party | Days | Date | Notes from River Lake
Secure Trip Date (Add to Spreadsheet in Yellow Box) | Host Church Team Leader & For the City |  |  | Done
Registration built in Landmark PCO | Landmark Administrator |  |  | Done and Live
Applications and Trip Roll Out | Host Church Team Leader | -150 | 2023-10-11 | Initial Informational meeting held 9/5
Applications due / Vetting Begins | Host Church Team Leader | -120 | 2023-11-10 | Complete
Deposits due | Host Church Team Leader & Landmark Administrator | -90 | 2023-12-10 | Done
Team Roster Set and Final payments dues | Host Church Team Leader & Landmark Administrator | -60 | 2024-01-09 | Done
Medical credentials and documents to field for medical team (if applicable) | GB Global Missions | -60 | 2024-01-09
Determine Special Projects based off Team Roster (if applicable) | Host Church Team Leader & For the City | -50 | 2024-01-19 | N/A
Determine Fun Day | Host Church Team Leader & For the City | -50 | 2024-01-19 | Nic working on this with Steve Gill
Send names and numbers (total, male, female) including ages to field | GB Global Missions | -45 | 2024-01-24
Ensure all ticket information is correct | Host Church Team Leader | -45 | 2024-01-24 | 1/14: Waiting to hear back from Dustin
Host Small Group Week 1 | Host Church Team Leader | -35 | 2024-02-03 | Every 5 days?
Host Small Group Week 2 | Host Church Team Leader | -30 | 2024-02-08
Ensure that all visas are seccured if required | GB Global Missions | -30 | 2024-02-08
Send out e-ticket information to team leader | GB Global Missions | -30 | 2024-02-08
Host Small Group Week 3 | Host Church Team Leader | -25 | 2024-02-13
Host Small Group Week 4 | Host Church Team Leader | -20 | 2024-02-18
Host Small Group Week 5 | Host Church Team Leader | -15 | 2024-02-23
Send food money and project money to field | GB Global Missions | -15 | 2024-02-23
Travel insurance obtained and cards sent to team leader | GB Global Missions | -15 | 2024-02-23
Team t-shirts sent to team leaders | GB Global Missions | -15 | 2024-02-23
Register team with US Department of State (SMART) | GB Global Missions | -15 | 2024-02-23
Send project money received less than 14 days prior to field immediately | GB Global Missions | -14 | 2024-02-24
Host Small Group Week 6 | Host Church Team Leader | -10 | 2024-02-28
Host Small Group Week 7 | Host Church Team Leader | -5 | 2024-03-04
Trip Date |  |  | 2024-03-09
Host Small Group Lesson 8 | Host Church Team Leader
Host Small Group Leson 9 | Host Church Team Leader
Fun Day | Activity ???
Share Recap Video at Church / Promo Next Trip | Host Church Team Leader | 8 | 2024-03-17
Host Small Group Week 10 | Host Church Team Leader | 12 | 2024-03-21
Formulas:
Date = SUM(D27,[Days])
Date = SUM([Date, row below],[Days])

## River Lake - Communication
Date | Communication | Number | Vehicle | Via
2023-11-02 | Pastor Nic - Welcome - registrants | 11 | Email | Mail Chimp
2023-11-13 | Pastor Nic - Schedule Meeting | 11 | Email | Mail Chimp
2023-11-15 | Jan - Q and A | 11 | Email | Mail Chimp
2023-12-05 | Jan - Confirmation of Meeting | 11 | Email | Mail Chimp
2023-12-06 | Kick off meeting | 11 | In Person | RLC
2023-12-07 | Jan - Follow up from meeting | 12 | Email | Mail Chimp
2023-12-11 | Jan - Proposed new schedule | 12 | Email | Mail Chimp
2023-12-19 | Jan - Confirm new schedule | 12 | Email | Mail Chimp
2024-01-03 | Jan - Remind mtg/Seth | 11 | Email | Mail Chimp
2024-01-06 | Seth-Passport/Document Reminder |  | Email | PC
2024-01-07 | Meeting |  | In Person | RLC
2024-01-08 | Seth-Final Payment Link |  | Email | PC
2024-01-20 | Meeting reschedule note |  | email | PC
2024-01-28 | meeting: Leadership wk 1/coin act. |  | in person | RLC
2024-01-31 | Meeting schedule change |  | email | PC
2024-02-02 | 2023 Video Recap Reveal |  | email | PC