## Sheet1
Action Item | Responsible Party | Days | Date | Notes
Secure Trip Date (Add to Spreadsheet in Yellow Box) | Host Church Team Leader & For the City |  |  | Done
Registration built in Landmark PCO | Landmark Administrator |  |  | Done
Applications and Trip Roll Out | Host Church Team Leader | -150 | 2024-02-07 | Done
Applications due / Vetting Begins | Host Church Team Leader | -120 | 2024-03-08 | Done
Deposits due | Host Church Team Leader & Landmark Administrator | -90 | 2024-04-07 | Done
Team Roster Set and Final payments dues | Host Church Team Leader & Landmark Administrator | -60 | 2024-05-07 | Done
Medical credentials and documents to field for medical team (if applicable) | GB Global Missions | -60 | 2024-05-07
Determine Special Projects based off Team Roster (if applicable) | Host Church Team Leader & For the City | -50 | 2024-05-17 | Done
Determine Fun Day | Host Church Team Leader & For the City | -50 | 2024-05-17
Send names and numbers (total, male, female) including ages to field | GB Global Missions | -45 | 2024-05-22
Ensure all ticket information is correct | Host Church Team Leader | -45 | 2024-05-22 | Done
Host Small Group Week 1 | Host Church Team Leader | -35 | 2024-06-01 | Done
Host Small Group Week 2 | Host Church Team Leader | -30 | 2024-06-06 | Done
Ensure that all visas are seccured if required | GB Global Missions | -30 | 2024-06-06
Send out e-ticket information to team leader | GB Global Missions | -30 | 2024-06-06
Host Small Group Week 3 | Host Church Team Leader | -25 | 2024-06-11 | Done
Host Small Group Week 4 | Host Church Team Leader | -20 | 2024-06-16 | Done
Host Small Group Week 5 | Host Church Team Leader | -15 | 2024-06-21 | Done
Send food money and project money to field | GB Global Missions | -15 | 2024-06-21
Travel insurance obtained and cards sent to team leader | GB Global Missions | -15 | 2024-06-21 | Done
Team t-shirts sent to team leaders | GB Global Missions | -15 | 2024-06-21 | Done
Register team with US Department of State (SMART) | GB Global Missions | -15 | 2024-06-21
Send project money received less than 14 days prior to field immediately | GB Global Missions | -14 | 2024-06-22
Host Small Group Week 6 | Host Church Team Leader | -10 | 2024-06-26 | Done
Host Small Group Week 7 | Host Church Team Leader | -5 | 2024-07-01
Trip Date |  |  | 2024-07-06
Host Small Group Lesson 8 | Host Church Team Leader
Host Small Group Leson 9 | Host Church Team Leader
Fun Day | Activity ???
Share Recap Video at Church / Promo Next Trip | Host Church Team Leader | 8 | 2024-07-14
Host Small Group Week 10 | Host Church Team Leader | 12 | 2024-07-18
Formulas:
Date = SUM(D27,[Days])
Date = SUM([Date, row below],[Days])