## Sheet1
Action Item | Responsible Party | Days | Date | Notes
Secure Trip Date (Add to Spreadsheet in Yellow Box) | Host Church Team Leader & For the City
Registration built in Landmark PCO | Landmark Administrator
Applications and Trip Roll Out | Host Church Team Leader | -150 | 2024-05-08
Applications due / Vetting Begins | Host Church Team Leader | -120 | 2024-06-07
Deposits due | Host Church Team Leader & Landmark Administrator | -90 | 2024-07-07
Team Roster Set and Final payments dues | Host Church Team Leader & Landmark Administrator | -60 | 2024-08-06
Medical credentials and documents to field for medical team (if applicable) | GB Global Missions | -60 | 2024-08-06
Determine Special Projects based off Team Roster (if applicable) | Host Church Team Leader & For the City | -50 | 2024-08-16
Determine Fun Day | Host Church Team Leader & For the City | -50 | 2024-08-16
Send names and numbers (total, male, female) including ages to field | GB Global Missions | -45 | 2024-08-21
Ensure all ticket information is correct | Host Church Team Leader | -45 | 2024-08-21
Host Small Group Week 1 | Host Church Team Leader | -35 | 2024-08-31
Host Small Group Week 2 | Host Church Team Leader | -30 | 2024-09-05
Ensure that all visas are seccured if required | GB Global Missions | -30 | 2024-09-05
Send out e-ticket information to team leader | GB Global Missions | -30 | 2024-09-05
Host Small Group Week 3 | Host Church Team Leader | -25 | 2024-09-10
Host Small Group Week 4 | Host Church Team Leader | -20 | 2024-09-15
Host Small Group Week 5 | Host Church Team Leader | -15 | 2024-09-20
Send food money and project money to field | GB Global Missions | -15 | 2024-09-20
Travel insurance obtained and cards sent to team leader | GB Global Missions | -15 | 2024-09-20
Team t-shirts sent to team leaders | GB Global Missions | -15 | 2024-09-20
Register team with US Department of State (SMART) | GB Global Missions | -15 | 2024-09-20
Send project money received less than 14 days prior to field immediately | GB Global Missions | -14 | 2024-09-21
Host Small Group Week 6 | Host Church Team Leader | -10 | 2024-09-25
Host Small Group Week 7 | Host Church Team Leader | -5 | 2024-09-30
Trip Date |  |  | 2024-10-05
Host Small Group Lesson 8 | Host Church Team Leader
Host Small Group Leson 9 | Host Church Team Leader
Fun Day | Activity ???
Share Recap Video at Church / Promo Next Trip | Host Church Team Leader | 8 | 2024-10-13
Host Small Group Week 10 | Host Church Team Leader | 12 | 2024-10-17
Formulas:
Date = SUM(D27,[Days])
Date = SUM([Date, row below],[Days])