## Sheet1
Action Item | Responsible Party | Days | Date | Notes
Secure Trip Date (Add to Spreadsheet in Yellow Box) | Host Church Team Leader & For the City |  |  | Trip Dates 11/1 through 11/8
Registration built in Landmark PCO | Landmark Administrator |  |  | Dustin has built and sent link
Applications and Trip Roll Out | Host Church Team Leader | -150 | 2024-06-04 | Announcing 4/7, initial info meeting on 4/29
Applications due / Vetting Begins | Host Church Team Leader | -120 | 2024-07-04
Deposits due | Host Church Team Leader & Landmark Administrator | -90 | 2024-08-03 | RLC preferred Date: 7/5/2024
Team Roster Set and Final payments dues | Host Church Team Leader & Landmark Administrator | -60 | 2024-09-02
Medical credentials and documents to field for medical team (if applicable) | GB Global Missions | -60 | 2024-09-02
Determine Special Projects based off Team Roster (if applicable) | Host Church Team Leader & For the City | -50 | 2024-09-12
Determine Fun Day | Host Church Team Leader & For the City | -50 | 2024-09-12
Send names and numbers (total, male, female) including ages to field | GB Global Missions | -45 | 2024-09-17
Ensure all ticket information is correct | Host Church Team Leader | -45 | 2024-09-17
Host Small Group Week 1 | Host Church Team Leader | -35 | 2024-09-27
Host Small Group Week 2 | Host Church Team Leader | -30 | 2024-10-02
Ensure that all visas are seccured if required | GB Global Missions | -30 | 2024-10-02
Send out e-ticket information to team leader | GB Global Missions | -30 | 2024-10-02
Host Small Group Week 3 | Host Church Team Leader | -25 | 2024-10-07
Host Small Group Week 4 | Host Church Team Leader | -20 | 2024-10-12
Host Small Group Week 5 | Host Church Team Leader | -15 | 2024-10-17
Send food money and project money to field | GB Global Missions | -15 | 2024-10-17
Travel insurance obtained and cards sent to team leader | GB Global Missions | -15 | 2024-10-17
Team t-shirts sent to team leaders | GB Global Missions | -15 | 2024-10-17
Register team with US Department of State (SMART) | GB Global Missions | -15 | 2024-10-17
Send project money received less than 14 days prior to field immediately | GB Global Missions | -14 | 2024-10-18
Host Small Group Week 6 | Host Church Team Leader | -10 | 2024-10-22
Host Small Group Week 7 | Host Church Team Leader | -5 | 2024-10-27
Trip Date |  |  | 2024-11-01
Host Small Group Lesson 8 | Host Church Team Leader
Host Small Group Leson 9 | Host Church Team Leader
Fun Day | Activity ???
Share Recap Video at Church / Promo Next Trip | Host Church Team Leader | 8 | 2024-11-09
Host Small Group Week 10 | Host Church Team Leader | 12 | 2024-11-13
Formulas:
Date = SUM(D27,[Days])
Date = SUM([Date, row below],[Days])

## RLC Communication
Date | Communication | Number | Vehicle | Via
| Friyay Email |  | Email
2024-04-07 | Announcement to church |  | Sunday Service | Host - Brock

## Team
Name: | Passport | FTC Waiver | Missions Agreements & Waivers | Special Skills
Seth Harper | Yes
Heather Harper | Yes
Eric Tarter | Yes
Sarah Johnson | Yes
Alisha Reeves | Yes
Becky Trent | Yes
Carol Griffin | Yes
Judy Cruz | Yes
Robbie Birdsell | Yes
Ashton Birdsell | Yes
Terry Payne | Yes
Kim Vogel | Yes